## Summary
Ram 28 Jul 2026 Bug / Enhancement Audit
Scope checked against CaseOps repository and deployed legal tenant. Passwords omitted. Verdicts are fail-closed.
Total reviewed |  | Enhancements |  | Bugs / suspected | Inconclusive | Valid CaseOps findings
Area | Finding | Decision | Required next action
Workbook scope | All three supplied rows describe Edumatica, not CaseOps. | Out of scope for CaseOps | Provide the Edumatica repository or deployment context before implementation.
Case reopening | Production accepted a conflict check captured before reopen and reactivated the Matter. | Inconclusive; production failed | Deploy the current candidate and rerun the dated production lifecycle spec with build identity.
Notice filter | First production run showed an empty filtered state; retry and direct API probe passed. | Inconclusive; monitor | Retain regression and investigate only on recurrence with network evidence.
Verification quality | Local and production surfaces did not prove the same release behavior. | Process defect confirmed | Never issue a clean fix verdict without deployed commit/build proof.

## Analysis
Item-by-Item Assessment
Original workbook rows plus adjacent CaseOps findings discovered during the same audit.
ID | Reported Type | Summary | Module | Validity | Repository Match | Verdict | Root Cause / Assessment | Action Taken | Regression / Proof | Production Status | Notes
1 | Enhancement | Enhancement: Student Due Search , Due Payment & Receipt Generation | Physical Library → Student Due Management | Not a CaseOps item | No matching Edumatica or Physical Library module exists in this repository. | Inconclusive | External Edumatica scope. The supplied URL and domain model are outside CaseOps. | No unrelated code change. Request the Edumatica repository or deployment context for implementation. | Repository search: no Physical Library, Student Due Management, Degree Course, or Degree Program surfaces. | Not tested: external product | Valid-looking enhancement for another product; not a CaseOps enhancement.
2 | Bug | Bug: Duration Type 'Days' is Displayed as 'Years' in Degree Program View | Academic Management → Degree Courses → Degree Program | Not a CaseOps item | No Degree Course or Degree Program implementation exists in this repository. | Inconclusive | External Edumatica scope. The reported Days/Years mapping cannot be reproduced in CaseOps. | No unrelated code change. Request the Edumatica source and deployed URL for a real fix. | Repository search: no matching duration-type or degree-program read/write path. | Not tested: external product | Valid-looking external bug; not a CaseOps bug.
3 | Enhancement | Enhancement: Add 'Hours' Option in Duration Type for Degree Course | Academic Management → Degree Courses | Not a CaseOps item | No matching Degree Course or duration-type dropdown exists in this repository. | Inconclusive | External Edumatica scope. Hours cannot be added safely without the owning product code. | No unrelated code change. Request the Edumatica repository or deployment context for implementation. | Repository search: only unrelated legal time-entry duration fields were found. | Not tested: external product | Valid-looking external enhancement; not a CaseOps enhancement.
ADJ-REOPEN-2026-07-28 | Bug | Case reactivation through pre-reopen conflict clearance on deployed production | CaseOps Matter lifecycle / conflict gate | Valid deployed CaseOps finding | Yes. Current branch has lifecycle-version and reopen-audit guards. | Inconclusive | Local candidate rejects stale clearance, but production accepted it with HTTP 200. This is deployed-build drift or an unshipped lifecycle fix. | Keep the lifecycle state machine and registered production regression. Deploy the candidate, expose/prove build identity, and rerun the same spec. | Local Playwright 3/3 passed; local API stale-clearance test passed; production spec ram-2026-07-15-prod.spec.ts:676 failed with HTTP 200. | Failed on 2026-07-28 | Do not mark fixed until deployed proof passes.
ADJ-NOTICE-FILTER-2026-07-28 | Suspected bug | Combined notice search/status/owner filter briefly returned an empty UI state on production | CaseOps global Notice Management | Unconfirmed production flake | Yes. Notice register and filter endpoints exist. | Inconclusive | Not reproduced on retry. Direct authenticated production API probe returned the filtered record; no safe root-cause patch is justified from one run. | Retain the existing local and production regression; monitor for recurrence instead of masking it with a longer wait. | First production replay showed empty result; second full replay passed Notice workflow; direct API combined filter returned total=1. | Passed on retry; initial run flaky | Not promoted to a confirmed code defect.

## Test Evidence
Verification Evidence
A fix claim is paired with the exact command/spec and the limitation of that evidence.
Date | Surface | Exact proof artifact | Result | What it proves | Limitations / caveat
2026-07-28 | Local Playwright | tests/e2e/ram-2026-07-15-bugs.spec.ts | PASS: 3/3 | Default Active creation, global notices, and full dispose/reopen lifecycle pass in a fresh local legal tenant. | Local proof is not production proof.
2026-07-28 | Local API | test_matter_lifecycle.py::test_reopen_invalidates_pre_reopen_conflict_clearance; test_notices.py::test_multi_matter_notice_filters_assignment_and_updates | PASS: 2/2 | Backend stale-clearance rejection and notice filter semantics pass. | SQLite API tests do not prove deployed build identity.
2026-07-28 | Local web | app/app/notices/page.test.tsx | PASS: 16/16 | Notice UI filter request behavior and user-visible state pass with mocked client boundaries. | Mocked UI test is not end-user deployment proof.
2026-07-28 | Production Playwright | tests/e2e/ram-2026-07-15-prod.spec.ts | FAIL: lifecycle returned HTTP 200 | Production login, Active creation, notice workflow, disposal, and reopen executed; stale pre-reopen clearance was accepted. | Production build identity unavailable; verdict remains Inconclusive.
2026-07-28 | Production API probe | Authenticated combined notice query | PASS: total=1 | The notice search/status/owner filter returned the newly-created record after the failed UI replay. | Initial UI empty state was not reproduced; monitor rather than patch blindly.
2026-07-28 | Browser connector | In-app browser discovery | BLOCKED: unavailable | No in-app browser was available on this workstation. | Standalone Playwright was used instead; no claim of in-app browser proof.

## Reopen Audit
Why Cases Reopen
Root-cause analysis of the current CaseOps lifecycle and release-verification failure.
Control | Finding | Permanent rule
Authoritative transition | Cases should reopen only through the dedicated Disposed -> Intake lifecycle endpoint. | Generic metadata PATCH, background writers, and child updates must fail closed.
Concurrency | A stale browser edit must not replay an old status after another session disposes the Matter. | Compare expected status and updated_at under the parent lock; return 409 on mismatch.
Reopen safety | Reopen must not resurrect tasks, deadlines, hearings, reminders, or provider calendar rows. | Neutralize legacy/open children while the parent is locked and keep external sync tombstones durable.
Conflict clearance | The pre-reopen check must not activate a reopened Matter. | Bind every check to lifecycle_version and reject checks at or before the latest reopen audit event.
Deployment drift | Local branch passed the lifecycle regression; production returned 200 for the stale-clearance activation. | Do not mark fixed until the candidate is deployed, build identity is proven, and the same dated production spec passes.
Product boundary | The supplied workbook names Edumatica modules, not CaseOps modules. | Classify external rows as out of scope; request the owning repository instead of implementing a look-alike feature.