## Summary
CaseOps Bug Fix Summary — Ram 28 Jul 2026
One workbook row was reviewed against CaseOps. Verdicts are fail-closed and production credentials/passwords are not recorded.
Workbook rows |  | Valid CaseOps bugs |  | Properly fixed | Release blockers | Inconclusive
Area | Finding | Decision | Evidence / next action
BUG-001 scope | Judge Aliases was implemented but missing from the shared Admin navigation registry. | Valid bug; properly fixed | Web candidate 7495bc6 deployed to 100% and production Playwright passed.
Regression breadth | Desktop sidebar and shared mobile drawer now expose the same capability-gated route. | Covered | Local and production dated specs assert navigation plus destination page.
Full deployment | The API migration job references missing revision 20260723_0001. | Release blocker | Repair migration lineage before the next API deployment; do not bypass the gate.

## Analysis
Item-by-Item Assessment
The workbook row is separated from an adjacent release blocker discovered while deploying and revalidating it.
ID | Record Type | Module | Reported Environment | Classification | Verdict | Reported Summary | Root Cause | Fix / Decision | Regression Proof | Deployment Evidence | Notes
BUG-001 | Workbook row | UI / Navigation | Admin & Governance | Valid CaseOps bug | Properly fixed | Judge Aliases feature is hidden from the Admin navigation/menu. | Shared Sidebar NAV registry omitted /app/admin/judge-aliases. The route, API, Admin landing-page action, and page tests already existed. | Added a capability-gated Judge aliases item to the shared Sidebar registry. Because SidebarBody is reused by the mobile drawer, both surfaces now stay aligned. | Desktop + mobile navigation and real destination page are covered by tests/e2e/ram-2026-07-28-bugs.spec.ts and tests/e2e/ram-2026-07-28-prod.spec.ts. | Candidate web image 7495bc6; Cloud Run revision caseops-web-00191-vn9 at 100% traffic. | Production proof passed with supplied tester account; password intentionally omitted.
DEPLOY-GATE-2026-07-28 | Adjacent release finding | Production migration job cannot locate database revision 20260723_0001. | Production deployment pipeline | Valid release blocker | Inconclusive | Canonical full deploy was blocked before API rollout because the production database points to an Alembic revision absent from the repository image. | gcloud run jobs execute caseops-migrate-job failed with exit code 255: Can't locate revision identified by '20260723_0001'. | Did not bypass the migration gate. Deployed only the web image because BUG-001 is web-only; API traffic was not changed. | Cloud Run job execution caseops-migrate-job-7mmw2; logs recorded in the deployment audit. | API image built but not deployed; web-only deployment succeeded. | Requires migration-lineage repair before the next full API release.

## Test Evidence
Verification Evidence
Every fixed verdict is paired with a repeatable user-visible proof artifact and deployed build identity.
Date | Surface | Exact proof artifact | Result | What it proves | Limitations / caveat
2026-07-28 | Focused web unit | apps/web/components/app/Sidebar.test.tsx | PASS: 5/5 | Capability-gated navigation includes Judge aliases for an allowed custom-role capability set. | Component test is not deployment proof.
2026-07-28 | Local Playwright | tests/e2e/ram-2026-07-28-bugs.spec.ts | PASS: 1/1 | Fresh local legal tenant: desktop sidebar and 360px mobile drawer both navigate to and render Judge Aliases. | Local build is not production proof.
2026-07-28 | Production pre-deploy Playwright | tests/e2e/ram-2026-07-28-prod.spec.ts | FAIL as expected | Reproduced the original defect: signed-in tester could not find the Judge aliases link before deployment. | Captured against the old production web revision.
2026-07-28 | Cloud Build | candidate commit 7495bc6; web image digest sha256:d1832f... | PASS | Production web artifact built with TypeScript/Next production build and pushed to Artifact Registry. | API image was also built but not deployed because migration gate failed.
2026-07-28 | Production web deployment | caseops-web-00191-vn9; image tag 7495bc6 | PASS: 100% traffic | The web-only fix is the live production revision. | Full canonical API rollout remains blocked by missing Alembic revision 20260723_0001.
2026-07-28 | Production Playwright | tests/e2e/ram-2026-07-28-prod.spec.ts | PASS: 1/1 | Supplied tester account: desktop sidebar, mobile drawer, destination URL, and Judge Aliases heading all passed on live caseops.ai. | Password omitted; API health proves availability only. Cloud Run image tag proves web candidate identity.
2026-07-28 | Migration gate | caseops-migrate-job-7mmw2 logs | BLOCKED: exit 255 | Prevented an unsafe API rollout; logs report missing revision 20260723_0001. | Requires a separate migration-lineage repair before a full deploy.

## Reopen Audit
Why Cases Reopen / Release Drift Audit
This batch did not introduce a new lifecycle bug, but the deployment investigation exposed why local fixes can appear to reopen in production.
Control | Finding | Permanent rule
User-visible scope | A route can exist and be linked from an Admin landing page while still being absent from the primary navigation registry. | Acceptance tests must start at the actual main navigation and cover desktop plus mobile when they share a primitive.
Root cause of BUG-001 | Sidebar NAV omitted /app/admin/judge-aliases; the page/API were already present. | Maintain one shared navigation registry and a regression that clicks the link and renders the destination.
Why fixes appear to reopen | Previous evidence can prove a local candidate while production continues serving an older or drifted build. | Pair every fixed verdict with the exact deployed image/revision and the same dated production Playwright spec.
Migration lineage | The full deploy was correctly stopped because production alembic_version points to absent revision 20260723_0001. | Never bypass the migration job; add release checks that the image contains every revision referenced by production before API rollout.
Fail-closed verdict | The web-only BUG-001 fix passed production, but the overall API/web release was not certified because the migration gate failed. | Separate item-level proof from release-level GO/NO-GO and record blockers in the summary.