## Summary
CaseOps Bug Fix Summary — Ram 29 Jul 2026
Two workbook rows were assessed against the CaseOps repository and live legal tenant. Production credentials are intentionally omitted. Fixed means the exact dated Playwright proof passed after the deployed image/revision was verified.
Workbook rows |  | Valid bugs |  | Fixed / revalidated | Prod Playwright pass | Lifecycle result
Area | Finding | Verdict | Evidence / next action
BUG-001 | Judge Aliases was missing from the shared Admin navigation registry; the page and landing-page action already existed. | Fixed / revalidated | Valid bug. Existing shared Sidebar fix retained; live desktop + mobile Playwright passed after fd1238c deployment.
BUG-002 | The Admin header nested eight actions inside a non-wrapping flex row; Provider ops extended 3.484px beyond a 360px viewport. | Fixed / revalidated | Valid bug. Admin action group and shared PageHeader slot now shrink/wrap; live 360px Playwright passed.
Case reopening | Disposed -> Intake is an intentional controlled transition; unexpected reactivation was not reproduced after deployment. | Lifecycle revalidated | Live lifecycle Playwright passed. Generic PATCH, stale writes, child resurrection, and operational-view leakage remained blocked.
Release discipline | The source tree and the running artifact had previously drifted, allowing a stale build to look like a reopened bug. | Permanent control added | Exact image tag/revision, migration gate, and same dated production spec are now required evidence.

## Item Assessment
Item-by-Item Assessment
Both source rows are valid CaseOps bugs. BUG-001 was a prior fix revalidation; BUG-002 required the responsive code change in fd1238c.
ID | Reported type | Module | Environment | Classification | Verdict | Reported summary | Root cause | Fix / disposition | Regression proof | Production identity | Notes
BUG-001 | UI / Responsive | Admin & Governance / Judge Aliases | Chrome desktop + Android-sized mobile | Valid bug | Fixed / revalidated | [Reopened] Judge Aliases section is hidden/not visible on the Desktop Admin page (Desktop). | The page, API, and Admin landing action existed, but the shared Sidebar NAV registry omitted /app/admin/judge-aliases. A stale local .next artifact also made the already-fixed source look broken during retest. | Retained the capability-gated shared Sidebar item. No duplicate page-specific navigation was added. Rebuilt the production web artifact and revalidated both navigation surfaces. | Local Playwright 2/2; production Playwright BUG-001 PASS after fd1238c. Existing Sidebar unit coverage also passes. | caseops-web-00194-5qt; image fd1238c; 100% traffic | Valid bug. The code fix predates this commit; this run closes the revalidation gap.
BUG-002 | Responsive UI | Admin & Governance / Admin landing page | Chrome Android-sized 360px viewport | Valid bug | Fixed / revalidated | Admin page content is hidden on Android after the Outlook section due to responsive UI issue. | AdminPage passed a single inner flex row as PageHeader actions. That inner row had no flex-wrap/min-width constraints, so its intrinsic width pushed Provider ops and later actions outside the viewport. | Added min-w-0/full-width/flex-wrap responsive constraints to the shared PageHeader action slot and Admin action group. This fixes the shared layout boundary rather than hiding individual links. | Pre-deploy production reproduced Provider ops right edge at 363.484px. Local production-build Playwright 2/2 and post-deploy production Playwright 2/2 passed. | caseops-web-00194-5qt; image fd1238c; 100% traffic | No API change; canonical migration/deploy gate still passed.

## Test Evidence
Verification Evidence
Evidence is separated by surface. Production proof includes the deployed identity and the exact Playwright spec; passwords are not recorded.
Date | Surface | Exact proof artifact | Result | What it proves | Limitations / caveat
2026-07-29 | Focused web unit | apps/web/components/app/Sidebar.test.tsx + app/app/admin/page.test.tsx | PASS: 12/12 | Capability filtering, Admin page actions, and existing UI contracts pass. | Unit tests are not deployment proof.
2026-07-29 | Web typecheck/build | npm run typecheck:web; npm run build:web | PASS | Current source typechecks and produces a fresh Next production build. | Local artifact must still be deployed and rechecked.
2026-07-29 | API lifecycle | apps/api/tests/test_matter_lifecycle.py | PASS: 16/16 | Terminal-state, CAS, lifecycle endpoint, child neutralization, and legacy-row controls pass. | SQLite/API test evidence is not live tenant evidence.
2026-07-29 | Local Playwright | tests/e2e/ram-2026-07-29-bugs.spec.ts | PASS: 2/2 | Judge Aliases desktop/mobile discoverability and all Admin action bounds at 360px pass on a fresh local legal tenant. | Local proof is not production proof.
2026-07-29 | Production pre-deploy Playwright | tests/e2e/ram-2026-07-29-prod.spec.ts | PASS: 1/2; BUG-002 FAIL | BUG-001 passed; BUG-002 reproduced live with Provider ops at 363.484px right edge before deployment. | This was the reproduction run, not a release sign-off.
2026-07-29 | Production deployment | fd1238c; caseops-api-00214-45z; caseops-web-00194-5qt | PASS | Cloud Build, migration job, recurring job repinning, 100% traffic, staleness sweep, health, and clamAV sidecar guard passed. | Health is availability evidence; image/revision is the release identity.
2026-07-29 | Production Playwright | tests/e2e/ram-2026-07-29-prod.spec.ts | PASS: 2/2 | Supplied tester account passed both workbook regressions after fd1238c reached 100% traffic. | Production credentials omitted from this workbook.
2026-07-29 | Production lifecycle Playwright | tests/e2e/ram-2026-07-15-prod.spec.ts | PASS: 3/3 | Active creation, notice flow, and full dispose/reopen lifecycle passed; stale writes and resurrection stayed blocked. | Created test records were returned to terminal state by the suite's cleanup.

## Why Cases Reopen
Why Cases Reopen
Brutal analysis: distinguish intentional lifecycle reopening from release drift and from child/status resurrection.
Control | Finding | Permanent rule | Evidence
Intentional transition | Disposed -> Intake is a controlled product action, not an accidental reopen. | Only the dedicated lifecycle endpoint may perform it; it requires expected status, updated_at, reason, and archive capability. | Production lifecycle spec PASS.
Generic metadata writes | A stale browser or generic PATCH must not replay Active after disposal. | Lock the parent and reject inactive/terminal metadata writes plus stale CAS tokens with HTTP 409. | Production lifecycle stale-write and generic reactivation assertions PASS.
Child resurrection | Tasks, deadlines, hearings, reminders, and provider rows can make a disposed case look operational even when the parent is terminal. | Dispose/reopen neutralizes open children, sets durable external tombstones, and blocks resurrection patches. | Production lifecycle child suppression/resurrection assertions PASS.
Release drift | A source fix can appear reopened when a stale .next or Cloud Run image is serving old code. | Build current source, verify exact image/revision, and run the same dated Playwright spec after deployment. | Local stale-build failure + Cloud Run fd1238c staleness sweep PASS.
Responsive drift | A nested flex row can hide later controls only at mobile widths while desktop appears healthy. | Mobile regressions assert every grouped action's rendered bounds, not only route existence. | Pre-deploy production reproduced 363.484px; post-deploy 360px proof PASS.
Process failure | Previous shallow fixes trusted a green local or partial proof and did not bind verdicts to a release artifact. | Fail closed: no 'fixed' label without code, test, deployment identity, production replay, and cleanup evidence. | Permanent rules added to AGENTS.md and docs/BUG_REOPEN_LEARNINGS_2026-07-29_RAM.md.

## Regression Matrix
Regression Matrix
These are the durable checks that prevent the same classes of bug from returning elsewhere in the product.
Regression area | Exact suite | Scenario | Expected invariant | Environment | Result
Admin navigation | tests/e2e/ram-2026-07-29-bugs.spec.ts / prod.spec.ts | Desktop + mobile Judge aliases navigation and destination render | Shared capability-gated route is visible, clickable, and destination heading renders | Local + production | PASS
Admin responsive actions | tests/e2e/ram-2026-07-29-bugs.spec.ts / prod.spec.ts | All eight Admin actions at 360px | Every action is visible, has the expected href, and stays within viewport bounds | Local + production | PASS
Terminal lifecycle | tests/e2e/ram-2026-07-15-prod.spec.ts | Dispose, stale edit, generic reactivation, child writes | 409 on unsafe writes; disposed stays out of Today/Calendar | Production | PASS
Controlled reopen | tests/e2e/ram-2026-07-15-prod.spec.ts | Disposed -> Intake -> Active with reload | Only dedicated lifecycle action reopens; cancelled children do not revive; Active persists | Production | PASS
Backend lifecycle suite | apps/api/tests/test_matter_lifecycle.py | State matrix, DB invariant, legacy rows, conflict history | 16 tests pass; status/is_active/lifecycle_version remain coherent | Local API | PASS

## Source Items
Source Workbook Rows
Copied from CaseOps_BugsRam29Jul2026.xlsx with the Credentials column intentionally excluded.
Bug ID | Severity | Type | Module | Sub Module | Page URL | Summary | Steps to Reproduce | Expected Result | Actual Result | Status | Environment | Reported By | Reported On | Screenshot
BUG-001 | High | UI / Responsive | Admin & Governance | Judge Aliases | https://caseops.ai/app/admin/judge-aliases | [Reopened] Judge Aliases section is hidden/not visible on the Desktop Admin page (Desktop). | 1. Login as Admin. 2. Open Admin & Governance. 3. Check available menu/options. 4. Observe that Judge Aliases option is not fully visible. 5. Access /app/admin/judge-aliases directly via URL. | Judge Aliases section should be fully visible and accessible on the desktop view. | Judge Aliases section is not fully displayed on the desktop page. | ReOpen | Chrome-Desktop (caseops.ai) | Ram | 2026-07-29
BUG-002 | High | Responsive UI | Admin & Governance | Mobile Responsive UI | https://caseops.ai/app/admin/ | Admin page content is hidden on Android after the Outlook section due to responsive UI issue. | 1. Login as Admin. 2. Open Admin & Governance. 3. Check available section/options. 4. Observe that after outlook option are not fully visible. 5. Access /app/admin/{section-name} directly via URL. | All Admin features available on desktop should also be visible and usable on Android (unless intentionally restricted). | The sections after Outlook are hidden/not displayed on Android due to a responsive UI issue. | Open | Chrome-Android (caseops.ai) | Ram | 2026-07-29